Appendix G – Gantt Chart: Consent in Motion (12-month timeline from ethical approval)

Shaded cells show the planned months of each activity. Timing matches Section 11 of the Research Protocol (Form 1). No data collection begins before written ethical approval. Principal investigator: Mutairah Alamlah Alshammari.

| Activity | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ethical approval (Jouf University Permanent Committee) and hospital permissions |  |  |  |  |  |  |  |  |  |  |  |  |
| Translation and back-translation of guides, invitations and consent forms |  |  |  |  |  |  |  |  |  |  |  |  |
| Pilot interviews (one woman, one nurse; excluded from sample) and guide refinement |  |  |  |  |  |  |  |  |  |  |  |  |
| Recruitment of women and interviews (in person 24–72 h after first mobilisation; telephone within 14 days of discharge) |  |  |  |  |  |  |  |  |  |  |  |  |
| Recruitment of nurses and physiotherapists and interviews |  |  |  |  |  |  |  |  |  |  |  |  |
| Verbatim transcription (within two weeks of each interview) |  |  |  |  |  |  |  |  |  |  |  |  |
| Concurrent contextual coding, memos and constant comparison (NVivo 14) |  |  |  |  |  |  |  |  |  |  |  |  |
| Independent coding of six transcripts and quotation checking |  |  |  |  |  |  |  |  |  |  |  |  |
| Group-by-pattern and contextual matrices; discrepant-case analysis |  |  |  |  |  |  |  |  |  |  |  |  |
| Interpretation, theory development and integration with literature |  |  |  |  |  |  |  |  |  |  |  |  |
| Fortnightly analytic discussions and audit trail (ongoing) |  |  |  |  |  |  |  |  |  |  |  |  |
| Progress reports and adverse-event reporting to the Committee (ongoing) |  |  |  |  |  |  |  |  |  |  |  |  |
| Manuscript preparation and COREQ reporting |  |  |  |  |  |  |  |  |  |  |  |  |
| Submission, dissemination and aggregated feedback to hospitals (if approved) |  |  |  |  |  |  |  |  |  |  |  |  |

Key: grey = preparation and ongoing governance; blue = data generation; light blue = transcription and analysis; yellow = independent coding check; green = interpretation; orange = reporting and dissemination.